## Insert Project Name
[Insert Project Name]
Training Plan

## Training Approach
As part of the PSO's Change Management methodology, the Training Strategy will aide in understanding impacted user groups and applying the appropriate training approach. The PSO recommends filling out this worksheet prior to, or alongside the Stakeholder Analysis and Communication Plan.
Directions: Summarize the overall training approach that will be applied to the project. See example below.

## Training Courses
|  |  | Format for Training Content |  |  |  |  | Audience
# | Training Courses / Topics | Content Available? | Power Point | Training Manual | Simulation | Prerequisite Courses | Duration (in Hours) | Audience A | Audience B | Audience C | Comments
100 | INTRODUCTION TO COURSE
Purpose and Objectives of this Course
200 | COMMITMENT CONTROL AND BUDGETING
Purpose and Objectives of this Course
300 | GENERAL LEDGER
Purpose and Objectives of this Course
400 | PURCHASING
Purpose and Objectives of this Course
500 | ACCOUNTS PAYABLE
Purpose and Objectives of this Course
600 | FINANCIAL REPORTING
Purpose and Objectives of this Course
JOB AIDS
| GPO | N |  | x |  |  | n/a | X
| London | N |  | x |  |  | n/a |  | X
| Prague | N |  | x |  |  | n/a |  |  | X
| Paris | N |  | x |  |  | n/a
| Madrid | N |  | x |  |  | n/a
| Accra | N |  | x |  |  | n/a
| Berlin | N |  | x |  |  | n/a
| Buenos Aires | N |  | x |  |  | n/a
| Shanghai | N |  | x |  |  | n/a
| Tel Aviv | N |  | x |  |  | n/a
| Florence | N |  | x |  |  | n/a
[6 empty] | Total Duration: | 0
| Total Training Topics (excluding Job Aids) | 0
| # of Training Topics where No Content Available | 0

## Training Topics Mapping (hidden)
Audience #: Estimated number of users for each Audience Group
Course # | Course Title (UPK TOC) | Course Title (Abu Dhabi fame Manual) | GPO | London | Prague | Paris | Madrid | Accra | Berlin | Buenos Aires | Shanghai | Tel Aviv | Sydney | Florence | Comments
Cash Management
Managing Cash Positions
Managing Fees and Transfers
Managing Settlements
Managing Bi-Lateral Netting
Managing Treasury Accounting Entries
Managing In-House Banking
Managing Investment Pools
Managing Facilities
Using Optimization
Administering Cash
Running Reports
Expenses
Maintaining Employee Profiles
Preparing Travel Authorizations
Preparing Cash Advances
Preparing Expense Reports
Processing Expense Report Exceptions
Preparing Time Reports and Time Adjustments
Using Commitment Control With Expenses
Managing Approvals in Expenses
Processing Expense Payments
Posting Expense Transactions
Viewing Accounting Transactions in Expenses
Running Reports
General Ledger
| Setting Up User Preferences |  | X | X | X | X | X | X | X | X | X | X | X | X
| Managing Journal Entries | Journals | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS
|  | Find an Existing Journal | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS
|  | Creating a Journal | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS
| Processing Journals | Posting a Journal | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS | JEMS
| Using Commitment Control |  | X | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA
Using Open Item Accounting
Using Interunit/Intraunit Accounting
| Processing Multiple Currencies |  | X | X | X | X | X | X | X | X | X | X | X | X
Processing Allocations
| Maintaining Budgets |  | X | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA | BIA
Calculating Average Balances
Managing Interim and Year-End Processing
| Running Reports | Running a Trial Balance | X | X | X | X | X | X | X | X | X | X | X | X
Payables
| Maintaining Vendors | Finding an Existing Vendor | X | X | X | X | X | X | X | X | X | X | X | X
Creating a New Vendor
| Entering Vouchers | Creating an AP Voucher | X | X | X | X | X | X | X | X | X | X | X | X
| Managing Vouchers |  | X | X | X | X | X | X | X | X | X | X | X | X
| Using Control Groups | Creating a Control Group | X | X | X | X | X | X | X | X | X | X | X | X
Add a New Control Group
Creating a Pay File
| Establishing Recurring Voucher Contracts |  | X | X | X | X | X | X | X | X | X | X | X | X
| Processing Payments | Creating a Manual Payment | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ? | ?
Petty Cash Payment
Batch Processing
| Inquiries |  | X | X | X | X | X | X | X | X | X | X | X | X
Running Financials and SCM Reports
Planning and Budgeting
Budgeting Overview
Designing the Planning Model
Using Flexible Formulas
Updating the Planning Model
Using the Planning Workspace
Using Line Item Activities
Using Mass Adjustments and Allocations
Using Position Budgeting
Using Asset Budgeting
Using Budget Analysis and Reporting
Project Costing
Introduction to PeopleSoft Project Costing
Maintaining Projects
Using Project Trees
Analyzing Projects
Managing Resource Transactions
Project Integration
Projects Integration with Asset Management
Projects Integration with General Ledger
Projects Integration with Procurement
Projects Integration with Time and Labor
Projects Integration with Expenses
Projects Integration with Third-Party Applications
Running Reports
Receivables
Introduction to Receivables
Maintaining Customers
Entering Receivables
Entering Payments
Applying Payments
Reviewing Payments
Payment Predictor
Account Aging and Communication
Credit, Collections, and Exceptions Management
Maintaining Receivables
Updating Receivables
Transferring Receivables
Exception and Collection Processing
Multiple Currencies
U.S Federal Systems
Running Reports
Reporting Tools for Financials and Supply Chain Management
| PeopleSoft Query Basics |  | X | X | X | X | X | X | X | X | X | X | X | X
| Defining Query Selection Criteria |  | X | X | X | X | X | X | X | X | X | X | X | X
| Advanced Query Options |  |  |  |  | X | [8 empty] | Note that Paris will need to build a query to export data for their SAGE system
Crystal Report Basics
Creating Crystal Reports
Formatting Crystal Reports
Advanced Crystal Report Options
PS/nVision Basics
PS/nVision Reporting on the Web
Financials and Supply Chain Management Fundamentals
| Navigating Overview |  | X | X | X | X | X | X | X | X | X | X | X | X
| Navigating To and Within Pages |  | X | X | X | X | X | X | X | X | X | X | X | X
| Using Keys and Search Pages |  | X | X | X | X | X | X | X | X | X | X | X | X
Working with Pages
Adding and Updating Data
Using PeopleSoft Workflow
Grants
Preparing and Submitting a Proposal
Managing Cost Sharing
Managing Awards and Projects
Applying Transactions to Grants
Preparing and Submitting a Protocol
Managing Award Billing
Managing Award Revenue
Managing Advances
Establishing Continuation Proposals
Performing Award Close Out Process
Running Reports
Contracts
Introduction to Contracts
Creating Contracts
Working with Milestones
Creating Billing Plans
Creating Revenue Recognition Plans
Booking and Managing Revenue
Amending a Contract
Renewing a Contract
Managing Accounting Distributions
Managing Contracts Billing
Creating and Managing Limits
Managing Contract Notes
Pricing Contracts
Processing Contracts Billing
Working with PeopleSoft Project Costing
Maintaining Support Teams
Managing Contracts
Working with Federal Reimbursable Agreements
Processing Prepaid Amounts
Running Financial and SCM Reports
Asset Management
Adding and Maintaining Assets
Maintaining Parent and Child Assets
Adjusting and Transferring Assets
Performing Physical Inventory
Working with Composite Assets
Working with Leased Assets
Working with Asset Budgeting
Retiring Assets
Archiving Asset Information
Depreciating Assets
Using User-Defined Depreciation
Creating Accounting Entries
Allocating Depreciation Expense
Integrating with Other Enterprise Applications
Changing Assets in Mass
Tracking Repairs and Service
Working with Joint Venture Processing
Running Financials and SCM Reports
Purchasing
|  | Creating a Purchase Order |  | X | X | X | X | X | X | X | X | X | X | X
|  | Approving a Purchase Order | X
|  | Dispatching a Purchase Order |  | X | X | X | X | X | X | X | X | X | X | X
|  | Change Orders | [12 empty] | placeholder in AD manual so need to develop content
Job Aids
| GPO |  | X
| London |  |  | X
| Prague |  |  |  | X
| Paris |  |  |  |  | X
| Madrid | [5 empty] | X
| Accra | [6 empty] | X
| Berlin | [7 empty] | X
| Buenos Aires | [8 empty] | X
| Shanghai | [9 empty] | X
| Tel Aviv | [10 empty] | X
| Sydney | [11 empty] | X
| Florence | [12 empty] | X

## Training Status (hidden)
Course # | Course Title | Development Status | [5 empty] | Reviewer/Approver |  | Delivery Owner |  | Delivery Status
|  | Draft Due | Draft Status | Review due | Review Status | Final Due | Final Status | Reviewer | Approver | Team | Individual | Date | Status | Makeup Date | Status
#REF! | #REF!
#REF! | #REF! | 2010-10-06 | Complete | 2010-10-11 | Complete | 2010-10-15 | Complete | N/A | Ufer | HR | Online | 2010-10-18 | Complete | TBD | Not Started
#REF! | #REF! | 2010-10-06 | Complete | 2010-10-11 | Complete | 2010-10-15 | Complete | N/A | Ufer | HR | Online | 2010-10-18 | Complete | TBD | Not Started
#REF! | #REF! | 2010-10-08 | Complete | 2010-10-12 | Complete | 2010-10-15 | Complete | N/A | Ufer | HR | Cruz | 2010-10-18 | Complete | TBD | Not Started
#REF! | #REF! | 2010-10-08 | Complete | 2010-10-12 | Complete | 2010-10-15 | Complete | N/A | Ufer | HR | Chavez | 2010-10-18 | Complete | TBD | Not Started

## Training Schedule
Training and Support Schedule A
Time | Monday | Tuesday | Wednesday | Thursday | Friday
AM |  |  | On Site Support
On Site Support
LUNCH
PM |  |  | On Site Support
Instructor-led Training (on site)
Training and Support Schedule B
Time | Monday | Tuesday | Wednesday | Thursday | Friday
AM
PM

## Training Timeline
January
|  |  | M | Tu | W | Th | F | M | Tu | W | Th | F | M | Tu | W | Th | F | M
# | Activity | Status
1 | Finalize training plan | bar: January M to January F
Confirm training modules | bar: January M to January M
Estimate duration for training delivery
Confirm facilitator(s)
Review training plan
Outline training delivery schedule
2 | Develop training materials
Create training manual
Create training PowerPoint
Test training in QA environment
Review and finalize training materials
3 | Prepare environment for training
Identify environment to use for training
Load/stage data
Create and test user IDs
Confirm support for environment
4 | Coordinate training logistics
Communicate training schedule to sites
Reserve space, if applicable
Print materials
Distribute materials
5 | Conduct UAT
Schedule dates and location
Create test scripts
Deliver UAT
Review results
6 | Prepare facilitator(s) for training delivery
7 | Deliver training (including on site support)
Key Dates
Pilot Go Live

## Training Schedule-by Site (hidden)
Site Name: GPO
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual
| 2011-02-14 | 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | On site
AM
PM
Time | Monday | Tuesday | Wednesday | Thursday | Friday
| 2011-02-21 | 2011-02-22 | 2011-02-23 | 2011-02-24 | 2011-02-25
AM
PM
Site Name: London
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual
| 2011-02-14 | 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | On site
AM
PM
Time | Monday | Tuesday | Wednesday | Thursday | Friday
| 2011-02-21 | 2011-02-22 | 2011-02-23 | 2011-02-24 | 2011-02-25
AM
PM
Site Name: Prague
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual
| 2011-02-14 | 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | On site
AM
PM
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual (e.g. video conference, webcast)
| 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | 2011-02-19 | On site
AM
PM
Formulas:
Tuesday = [Monday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1

## Training Schedule-Pilot Detail (hidden)
Site Name: London
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual
| 2011-02-14 | 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | On site
9:00
9:30
10:00
10:30
11:00
11:30
12:00
12:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
Time | Monday | Tuesday | Wednesday | Thursday | Friday
| 2011-02-21 | 2011-02-22 | 2011-02-23 | 2011-02-24 | 2011-02-25
9:00
9:30
10:00
10:30
11:00
11:30
12:00
12:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
Site Name: Prague
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual
| 2011-02-14 | 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | On site
9:00
9:30
10:00
10:30
11:00
11:30
12:00
12:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
Time | Monday | Tuesday | Wednesday | Thursday | Friday | Virtual (e.g. video conference, webcast)
| 2011-02-15 | 2011-02-16 | 2011-02-17 | 2011-02-18 | 2011-02-19 | On site
9:00
9:30
10:00
10:30
11:00
11:30
12:00
12:30
1:00
1:30
2:00
2:30
3:00
3:30
4:00
4:30
Formulas:
Tuesday = [Monday]+1
Wednesday = [Tuesday]+1
Thursday = [Wednesday]+1
Friday = [Thursday]+1

## Modification History
Version # | Date | Modified By | Modification Description
v1 | 2011-01-01 | Tom Smith | Created original draft
v2 | 2011-01-01 | Tom Smith | Updated with stakeholder comments